## About
Template | The gap plan template
From | OSFI E-23 for AI Systems, Chapter 11
Author | Dr. Nabeel A. Khan
Publisher | iSystematic Inc.
Version | 1.1, 18 October 2026
Web | nabeelkhan.com/e-23/gap-plan
Statements | Conformance with any framework named here is self-declared. OSFI does not endorse, approve or recommend this book or its templates. Coldbrook, Thornbury and Pellbrook are fictional.
How to use | Every column and rule is set out in the chapter named above, which is the method. One sheet per table in the template; the Word file carries the full text.
Licence | Licensed under the Companion Working Files Licence 1.0 (nabeelkhan.com/terms#companion-files). You may complete, adapt and use this file inside your own organisation, including commercially, and you may have an AI assistant help you complete it. You may not sell it, or republish it as a template set. Keep this credit line in the document.

## Part A. The plan one line
# | System | Gap, by kind | Chapter that surfaced it | Comes from (altitude) | Closed at (altitude) | Owner: one name, a person | Date | Evidence that will show it closed | Closed on (date) | Revised date, signed by the owner (where past its date)
P1
P2
P3

## The rules for each column
Column | Rule | Basis
System | One system per line, so that the plan can be read per system and across the portfolio | The discipline's (Chapter 11, the board pages)
Gap, by kind | One of the kinds in Part B, sorted by where the gap sits, not by who noticed it | The discipline's
Comes from | The altitude to which the expectation the gap leaves unmet belongs. It decides the date | The discipline's
Closed at | The smallest altitude at which closing the gap holds, smallest meaning nearest the running system. It decides the owner. No gap closes at the Regulatory Floor itself | The discipline's
Owner | One name, and a person, at every line. The discipline sets that rule where the guideline leaves room: E-23 allows the Model Approver to be a unit, an individual or a committee, and one name is the discipline's choice, never E-23's requirement | The discipline's
Date | Three sources, in order of authority. First, the guideline's own calendar: it takes effect on 1 May 2027, and on the book's reading every line whose gap comes from the Regulatory Floor is dated on or before that day. Second, the institution's own risk rating: a gap on a high-rated system is dated earlier than the same gap on a low-rated one. Third, a finding that a system's model risk sits outside the institution's risk appetite, for which the guideline expects remediation actions to be established: the date is the remediation's, not the plan's | E-23; the ordering and the Floor rule are the book's reading
Date, for a data gap | E-21 expected full adherence by 1 September 2026, with section 4, which carries its data risk management expectations, due a year earlier. A data gap dated against 1 May 2027 was, on the E-21 calendar, due before the plan was written, and the line should say so | E-21
Evidence that will show it closed | A record, not a say-so. "The control is in place" closes on someone's say-so; "the build emits the model version on every call and the retention is ninety days" closes on a record. Before 1 May 2027 the column says what will exist; after it, what does | The discipline's
Closed on | A closed line is retained: it is evidence that the gap was seen, owned and closed on a date. A deleted line is evidence of nothing | The discipline's
Revised date | A line past its date carries its owner's name and a new date that owner has signed | The discipline's (the board's per-system page)

## Part B. Kinds of gap, and
Kind | Chapter | The gap | Comes from | Closed at | Why
Scope | 1 | A system that meets the guideline's definition of a model, carries non-negligible inherent risk, and is not on the inventory, or is on it without a rating | Regulatory Floor | Operational Machinery | The expectation to inventory and rate comes from outside the institution; the inventory and its ratings are standing machinery
Evidence | 2 | A system for which the institution can say who approved it and cannot produce what they approved it on | Operational Machinery | Technical Substrate | The record of the institution's decisions is machinery; what fills it is emitted by the build
Validation | 3 | A validation record that claims more than the method could establish | Operational Machinery | Operational Machinery | Validation is a standing review; its record is rewritten to claim only what the method established
Control | 4 | A control that is neither a boundary the substrate enforces nor an optimization anyone tunes | Technical Substrate | Technical Substrate | A boundary the substrate cannot enforce is not a control
Unpassed gate at G3 | 5 | A gate the system never passed in a form the accountable person would sign | Strategic Compass | Strategic Compass | Approval is where the institution chooses; a system with no approver has had no choice made about it
Unpassed gate at G1, G2, G4 or G5 | 5 | A gate the system never passed in a form the accountable person would sign | Operational Machinery | Operational Machinery | The gate record is a standing process and the accountable person is a standing role
Adjacency | 6 | Records that exist and do not compose into one story | Operational Machinery | Operational Machinery | One shape for evidence is a rule the governance function sets and keeps
Authority | 7 | A faculty of an agent whose authority no contract states | Operational Machinery | Operational Machinery, then Technical Substrate | The contract for each faculty is written by the Machinery and enforced by the Substrate
Data | 8 | A retrieval system that cannot state the lineage or classification of what it retrieves | Technical Substrate | Technical Substrate | Lineage and classification are properties of the pipeline, or they are nothing
Vendor | 9 | A third-party model with a score and no recorded gate decision | Regulatory Floor | Operational Machinery | The obligation did not transfer with the contract; it is met by a gate decision, contract terms and the institution's own outcome test
Trigger | 10 | A revalidation trigger with no threshold, no owner, or no alert behind it | Operational Machinery | Technical Substrate and Operational Machinery | The alert lives in the build; the person who answers it lives in the governance office

## Part C. The four altitudes
Layer | Altitude | Definition, in the specification's words
1 | Regulatory Floor | "The minimum binding obligation boundary: the set of obligations the institution shall satisfy to operate its AI systems lawfully and licitly across every jurisdiction it operates in and under every binding authority source whose determination is a precondition of deployment."
2 | Strategic Compass | "The institution's deliberate choices about which AI it will build, at what level of accepted risk, and to what competitive end, made inside the Layer 1 boundary."
3 | Operational Machinery | "The standing institutional machinery that converts Layer 2 intent into Layer 1 compliance for every AI system across its full lifecycle."
4 | Technical Substrate | "The engineering that makes runtime-dependent Layer 3 controls enforceable inside the systems themselves."

## D.1 The portfolio page
# | System | Rating | Gate status | Open gaps and their owners | Triggers fired since the last report
B1
B2

## D.2 The page per system
# | Section | Entry
B3 | Lines closed since the last report, each with its evidence
B4 | Lines past their date, each with its owner's name and a new date that owner has signed
B5 | Regulatory Floor lines still open against 1 May 2027
B6 | Strategic Compass lines, by name: each a decision about accepted risk that someone senior must sign